## Risk and Issue Register
PMO Risk Issue and Action Item Register
PMO Name: | [6 empty] | PMO Leader:
Risk and Issue Identification |  |  | Quantitative Rating |  |  | Response Protocol
Description | Symptoms | Category | Probability | Severity | Risk Ranking | Strategy | Response | Trigger | Owner | Status
If this happens, then this will happen… | Indicate symptoms that will help you recognize the root cause risk or issue | Risk | 1 | 3 | Medium | Enhance (+) | Enter details about how you will respond to this risk or issue | We will know the risk has become an issue when…
If the PMO is setup for the wrong reasons, then it will not be sustainable. | Keeping up with the competition Latest articles say, “you need a PMO” The company is in chaos Everyone else is doing it | Risk | 2 | 3 | High
If the PMO type is established incorrectly, the PMO will not meet the business needs. | PMO leader assumes they know best PMO leader creates a cookie cutter PMO Rinse and repeat what works elsewhere Convincing leaders they need the PMO | Risk | 2 | 1 | Low
If the PMO value proposition is not clear, the PMO will become extinct. | Spending months/years “building” the PMO Perception of the PMO is slow and a barrier to progress PMO seen as overhead – expense vs. value driven Lost in an “Agile” world They don’t know the PMO exists PMO has trouble getting funding | Risk | 1 | 3 | Medium
If the PMO abuses methodology or relies too heavily on tools and process to show value, the PMO will not be able to deliver IMPACT. | Big focus on templates process before any value achieved Projects are getting lost in templates and process PMs are seen as box checkers You hear “your process” instead of “our process” Staff avoids the PMO – “our project doesn’t need the PMO” | Risk |  |  | Low
If the PMO puts too much emphasis on tools, then it will cease to deliver IMPACT. | Tools are difficult to use Real data is outside the system People avoid using them or treat as an out of process task Tools are homegrown or extremely customized The tool becomes a top priority in early PMO implementation | Risk |  |  | Low
If the PMO is a micromanging organization, then PM progress will be stifled and staff will not engage leading to PMO disaster. | Thinking the PMO has to own “everything project management” Getting involved in project minutia Ignoring everything that doesn’t fall into PMO scope Thinking all PMs must report into the PMO | Risk |  |  | Low
If the PMO is seen as a threat, then it will not get the engagement required to succeed. | Staff avoids engaging with the PMO PMO has a “hammer” approach to compliance PMO very focused on the “PMO way” or the highway Lack of coaching and mentoring services PMO is in the finger pointing business | Risk |  |  | Low
If the PMO is not placed in the right organizational structure/level, it will not have the required support and authority to drive transformation. | Staff ignores any PMO mandates or guidance Key sponsorship is missing to help influence change Organizational change management techniques not leveraged PMO established by a business unit to “defend” projects PMO regularly on the “chopping block” PMO doesn’t have buy-in from functional / senior managers | Risk |  |  | Low
If the PMO does not have an effecive communication strategy, then it will cease to drive effective IMPACT delivery. | Decisions are taking too long to get made Sponsors are down in the weeds of projects Stakeholders aren’t acting or delivering their work People aren’t acting in a prioritized way It takes several meetings to make progress / get decisions | Risk |  |  | Low
If the stakeholders are not effectively trained and supported to engage with the PMO, then they cannot assist in driving high-IMPACT project delivery. | Sponsors don’t understand their role or aren’t engaged Sponsors aren’t championing your change or solving problems All PMO staff and PMs are the same – no diversity in strengths Consultants are driving all PM and PMO transformation | Risk |  |  | Low
If the PMO does not have proper PMO measurements in place to show the IMPACT the PMO is making, then the PMO will not have value in the organization. | Stakeholders don’t “get” the PMO value All measurements focused on project performance Wrong projects are getting done Can’t get support or engagement Decisions aren’t happening in a timely manner | Risk |  |  | Low
If the PMO staff do not apply effective organizational change management techniques to support the culture through transformation, then the roadblocks and change resistance will prevent the PMO from delivering IMPACT. | Significant change resistance to the PMO Excuses for not engaging with the PMO “Can’t do that here” language PMO is pigeon holed for only certain projects No one “gets” the PMO Say one thing and do another | Risk |  |  | Low
Low
Low
Low
Low
Low
Low
Low
Low
Low
Low
Low
Low
KEY:
RISK - cause of the risk, the risk, and the effect that the risk causes to the project; what is it that you are working to avoid, decrease the impact of, or reduce the likelihood of occurring?
RISK CATEGORY - by area of project affected, source of risk or other useful category; what planning objective does this event affect?
PROBABILITY - likelihood that the risk will happen (on a scale of 0 to 3, with 3 being the hightest)
Severity - impact of the risk on the project if the risk occurs (on a scale of 0 to 3, with 3 being the hightest)
RISK SCORE - probability * severity
RISK RANKING - ranking of risks by risk score
RISK RESPONSE - what will be done if risk happens. There are four possible responses:
1.Avoid: Plan a response that will eliminate the risk before it occurs.
2.Transfer: Shift the risk to a third party.
3.Mitigate: Plan a response that will reduce the probability of the risk occurring and/or its impact on project outcomes.
4.Accept: If the risk is inevitable, it might not be worth the effort to attempt to prevent it.
TRIGGER - indicates risk has occurred or is about to occur
RISK OWNER - the person assigned to watch for risk triggers & responsible for risk response. Risk owner is assigned by PM

## Data (hidden)
Type | IRA | Focus | Measure | Strategy | Status
Threat | Issue |  | 1 | Avoid (-) | Response Planning
Opportunity | Risk |  | 2 | Transfer (-) | Monitoring
| Action |  | 3 | Mitigate (-) | Resolving (Issue)
|  |  |  | Accept (- or +) | Addressing (Risk)
|  |  |  | Exploit (+) | Closed
Share (+)
Enhance (+)
N/A (Issue)