## RACI Matrix
RACI Matrix
Last Updated Date:
Project Name: | [11 empty] | Legend
Project Manager: | [11 empty] | R |  | A |  | C |  | I
Sponsor: | [11 empty] | Responsible |  | Accountable |  | Consulted |  | Informed
| Project Leadership |  |  |  | Project Team Members |  |  |  |  | Project Sub-Teams |  |  |  |  | External Resources
| <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name>
| Project Sponsor | Steering Committee/ Board, etc. | Advisory Committee | Role #5 | Project Manager | Tech Lead | Functional Lead | SME | Project Team Member | Developer | Administrative Support | Business Analyst | Role #4 | Role #5 | Consultant | PMO | Role #3 | Role #4 | Role #5
Discovery Phase
Determine Operations vs Project using Checklist
Conduct Project Level Assessment
Submit New Project Intake Worksheet
Request Review by PMO
Develop Business Case
Create Executive Dashboard
Initiation Phase
Create Project Charter
Create Staffing Plan
Develop Staffing Roles & Responsibilites
Prepare Kick-off Meeting Agenda
Create Status Reports/Executive Dashboard
Planning Phase
Hold Project Kick-off Meeting; record Action Items - Minutes
Create WBS, Schedule, Budget Planning Worksheet
Create Additional Project Management Plans as required (Communication, Quality, Change Management, Benefits Realization, etc.)
Create Registers: Risk, Issue, Benefits
Create Status Reports/Executive Dashboard
Delivery Phase
Build Deliverables
Perform Change Management
Control & Monitor (Risk & Benefits Register, Issue Log; Change Request & CR Log)
Create Transition Plan
Create Status Reports/Executive Dashboard
Closure Phase
Create, conduct & document Lessons Learned, Project Management Evaluation
Implement Transition Plan
Implement Project Closure (Document Archive, Project Closure Checklist, etc.)
Release Staff
Project Acceptance
Create Status Reports/Executive Dashboard
Value Phase
Conduct periodic Benefits Realization assessments
Develop Benefits Realization Report
Create Status Reports/Executive Dashboard
Instructions for the RACI Matrix:
The RACI Matrix is a powerful tool to assist in the identification of roles and assigning of cross-functional responsibilities to a project deliverable or activity. RACI represents: R - Responsibility, A - Accountable, C - Consulted, and I - Informed RACI Definitions: Responsibility = person or role responsible for ensuring that the item is completed Accountable = person or role responsible for actually doing or completing the item Consulted = person or role whose subject matter expertise is required in order to complete the item Informed = person or role that needs to be kept informed of the status of item completion | [9 empty] | Simply place an R, A, C, I or any appropriate combination in each of the applicable roles for each activity. Modify as appropriate for your organization. Each Activity should have at least one individual Accountable while there may be shared responsibilities depending on the activity.
NOTE: IMPACT Engine Project Management Life Cycle templates are noted in BOLD
Role
Project Deliverable
(or Activity)

## Example
RACI Matrix
Last Updated Date:
Project Name: | [11 empty] | Legend
Project Manager: | [11 empty] | R |  | A |  | C |  | I
Sponsor: | [11 empty] | Responsible |  | Accountable |  | Consulted |  | Informed
| Project Leadership |  |  |  | Project Team Members |  |  |  |  | Project Sub-Teams |  |  |  |  | External Resources
| <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name> | <Name>
| Project Sponsor | Steering Committee/ Board, etc. | Advisory Committee | Role #5 | Project Manager | Tech Lead | Functional Lead | SME | Project Team Member | Developer | Administrative Support | Business Analyst | Role #4 | Role #5 | Consultant | PMO | Role #3 | Role #4 | Role #5
Discovery Phase
Determine Operations vs Project using Checklist | I |  |  |  | R/A
Conduct Project Level Assessment | C |  |  |  | R/A | A/C | A/C | C |  |  |  | C |  |  | C | A/C
Submit New Project Intake Worksheet | R/A |  |  |  | R/A | A/C | A/C | C
Request Review by PMO |  |  |  |  | R | [10 empty] | A
Develop Business Case | A/C | I | I |  | R/A | C | C | C |  |  |  | C |  |  | C | C
Create Executive Dashboard | I | I | I |  | R/A | R/A | R/A | R/A | C | C | C | C |  |  | A | I
Initiation Phase
Create Project Charter | C |  |  |  | R/A | C | C | C |  |  |  | C |  |  | C
Create Staffing Plan | I | I | I |  | R/A | C | C | C | C | C | C | C |  |  | C | I
Develop Staffing Roles & Responsibilites | I | I | I |  | R/A | C | C | C | C
Prepare Kick-off Meeting Agenda |  |  |  |  | R/A | C | C
Create Status Reports/Executive Dashboard | I | I | I |  | R/A | R/A | R/A | R/A | A | C | C | C |  |  | A | I
Planning Phase
Hold Project Kick-off Meeting; record Action Items - Minutes | C |  |  |  | R/A | R/A | R/A | C | C
Create WBS, Schedule, Budget Planning Worksheet | I | I | I |  | R/A | R/A | R/A | C | C | C | C | C |  |  | C | I
Create Additional Project Management Plans as required (Communication, Quality, Change Management, Benefits Realization, etc.) | I | I | I |  | R/A | R/A | R/A | A | C | I | I | I |  |  | C | I
Create Registers: Risk, Issue, Benefits | C | I | I |  | R/A | R/A | R/A | A | C | C | C | C |  |  | C | I
Create Status Reports/Executive Dashboard | I | I | I |  | R/A | R/A | R/A | A | A | C | C | C |  |  | A | I
Delivery Phase
Build Deliverables | C/I | C/I | C/I |  |  | R/A | R/A | R/A | R/A | R/A |  |  |  |  | A/C
Perform Change Management | C | C | C | [11 empty] | C | I | bar: R/A to C
Control & Monitor (Risk & Benefits Register, Issue Log; Change Request & CR Log) | A/C/I | C/I | C/I |  | R | A | A | A | A | C |  | C |  |  | C | A/C/I
Create Transition Plan | C/I | C/I | C/I | bar: R/A to C
Create Status Reports/Executive Dashboard | I | I | I |  | R/A | R/A | R/A | R/A | A | I | I | I |  |  | A | I
Closure Phase
Create, conduct & document Lessons Learned, Project Management Evaluation | C | C | C |  | R/A | C | C | C | C | C | C | C |  |  | C | C
Implement Transition Plan | I | I | I |  | R/A | A | A | A | C | C |  | A |  |  | A
Implement Project Closure (Document Archive, Project Closure Checklist, etc.) | I | I | I |  | R/A | A | A | A | C | A | A | A |  |  | A
Release Staff | R/A | I | I |  | R/A: R/A; R/A: A; R/A: A
Project Acceptance | R/A | A | A |  | R/A | A | A | A | A | [5 empty] | A | A
Create Status Reports/Executive Dashboard | I | I | I |  | R/A | R/A | R/A | R/A | A | C | C | C |  |  | A | I
Value Phase
Conduct periodic Benefits Realization assessments | C | I | I |  | R/A: R/A
Develop Benefits Realization Report | R/A | I | I |  | R/A: R/A
Create Status Reports/Executive Dashboard | I | I | I |  | R/A: R/A |  |  |  | I
Instructions for the RACI Matrix:
The RACI Matrix is a powerful tool to assist in the identification of roles and assigning of cross-functional responsibilities to a project deliverable or activity. RACI represents: R - Responsibility, A - Accountable, C - Consulted, and I - Informed RACI Definitions: Responsibility = person or role responsible for ensuring that the item is completed Accountable = person or role responsible for actually doing or completing the item Consulted = person or role whose subject matter expertise is required in order to complete the item Informed = person or role that needs to be kept informed of the status of item completion |  |  |  |  | I: Simply place an R, A, C, I or any appropriate combination in each of the applicable roles for each activity. Modify as appropriate for your organization. Each Activity should have at least one individual Accountable while there may be shared responsibilities depending on the activity.
NOTE: IMPACT Engine Project Management Life Cycle templates are noted in BOLD
Role
Project Deliverable
(or Activity)