## Proj Level Assess
Project Sponsor:
Project Level Assessment |  |  | Project Manager:
Project:
Project Level | Small (add 1) | Medium (add 2) | Large (add 3) | Score
Score Value
Strategic Impact | 0 | 0 | 0 | 0
Work Effort (hours) | 0 | 0 | 0 | 0
Expected Duration | 0 | 0 | 0 | 0
Scope | 0 | 0 | 0 | 0
Technology | 0 | 0 | 0 | 0
Organizational Impact | 0 | 0 | 0 | 0
Complexity | 0 | 0 | 0 | 0
Departments (including vendors) | 0 | 0 | 0 | 0
TOTAL SCORE | Small (1-10) | Medium (11-20) | Large (20+) | 0
Instructions: Leveraging a scalable methodology that considers size on multiple levels, the assessment will assist in the development of the right level of project management process based on the impact of the project. Consider all the factors listed down the left side of the assessment scale using the suggested definitions on the Example sheet. Adjust the definitions as appropriate for your organization. Assign values of 1 for Small projects, 2 for Medium projects, and 3 for Large projects for each category, except the number or department/vendors affected. The resulting total value derived will aid in determining the relative size of a project effort, the relative size of the project (small, medium or large), and the extent to which project management practices should be formally applied to the project.

## Example
Project Sponsor:
Project Level Assessment |  |  | Project Manager:
Project:
Project Level | Small (add 1) | Medium (add 2) | Large (add 3) | Sample Score for Project X
Score Value
Strategic Impact | None | Small | Large | 1
Work Effort (hours) | >80-200 | >200-499 | 500+ | 1
Expected Duration | 1-2 months | 3-6 months | 6+ months | 1
Scope | Minimal process or system change | Multiple process or system changes, but still internal focus | Requiring technology, product changes or broad organization impact | 3
Technology | In-house expertise | Existing | New or requires system-wide change/training | 2
Organizational Impact | Internal/Operational | Strategic/Board/ MBE | External, Organization-wide or external/member impact | 1
Complexity | Well-defined solution; no problems expected | Solution is known; some problems expected | Solution is unknown or not clearly defined | 1
Departments (including vendors) | 1-2 | 2-4 | >5 | 2
TOTAL SCORE | Small (1-10) | Medium (11-20) | Large (20+) | 12
Instructions: Leveraging a scalable methodology that considers size on multiple levels, the assessment will assist in the develop ent of the right level of project management process based on the impact of the project. Consider all the factors listed down the left side of the assessment scale using the suggested definitions on the Example sheet. Adjust the definitions as appropriate for your organization. Assign values of 1 for Small projects, 2 for Medium projects, and 3 for Large projects for each category, except the number or department/vendors affected. The resulting total value derived will aid in determining the relative size of a project effort, the relative size of the project (small, medium or large), and the extent to which project management practices should be formally applied to the project.